## Sheet1
Plan Details | Start Date | End Date | % of completion responsible | WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7
Project Planning: Assigning Roles & Wireframing | 19/03/2024 | 26/03/2024 | 20%
Frontend Development | 27/03/2024 | 2024-10-04 | 35%
Backend Development & Database Schema | 2024-11-04 | 20/04/2024 | 30%
Testing & User Feedback | 21/04/2024 | 25/04/2024 | 10%
Launch & Presentation | 26/04/2024 | 2024-04-05 | 5%